# PROJECT ESTIMATION, SCHEDULE & BUDGET MANAGEMENT PLAN

For PharmaCart - Omni-Channel Pharmacy Ordering Platform

Document Reference: EST-PLAN-PC-2026-V1.0

# Document Control & Metadata

- Project Name: PharmaCart — Online Ordering for Neighbourhood Pharmacy Chain

- Case Study Reference: Case Study No. 68

- Document Standard: PMI Project Management Body of Knowledge (PMBOK 7th Edition) & Agile Scrum Practice Guide

- Author / Lead Project Manager: Ritesh Jadhav

- Engineering Organization: PharmaCart Project Delivery Team

- Target Network: 14 Retail Pharmacies across Ahmedabad, Gujarat, India

- Date of Issue: October 2026

- Status: Baseline Approved (Approved by Pharmacy Chain Owner & Steering Committee)

# Revision History

| Version | Date | Author | Description of Change | Approved By |
| --- | --- | --- | --- | --- |
| 0.1 | 2026-1 0- 02 | Ritesh Jadhav | Initial story point estimation and backlog sizing | Engineering Team & Scrum Master |
| 0.5 | 2026-1 0- 03 | Ritesh Jadhav | Sprint runway, budget burn analysis, and CPM draft | Finance Controller & Owner |
| 1 .0 | 2026-1 0- 05 | Ritesh Jadhav | Finalized release scope, WBS, Gantt schedule, and baseline | Managing Director & Owner |

Table of Contents

- Executive Summary & Baseline Constraints

- Mathematical Estimation Models & Intermediate Calculations

  - Velocity & Sprint Duration Sizing

  - Sprints Calculation: Full Wishlist vs. Core MVP

  - Budget Runway & Burn Rate Computation

  - Feasibility Trade-Off Matrix

- Scope Decision & Scoping Justification

- Estimation Epistemology: Why an Estimate is NOT a Promise

  - The Cone of Uncertainty

  - Known Technical & Organizational Variances

  - Commitments vs. Forecasts in Agile Engineering

- Work Breakdown Structure (WBS)

- Critical Path Method (CPM) & Network Analysis

  - Precedence Table & Activity Attributes

  - Forward Pass & Backward Pass Calculations

  - Activity-on-Node (AON) Network Diagram

- Gantt Chart & Resource Allocation Schedule

- Sprint-by-Sprint Release Plan

- Budget Burn Runway & Financial Cash Flow Analysis

- Executive Summary & Baseline Constraints

The PharmaCart initiative operates under fixed contractual parameters defined by the chain owner:

- Total Available Capital Budget: ₹14,00,000 (₹14.0 Lakh).

- Maximum Delivery Horizon: 5 Calendar Months (21.7 Weeks / ~152 Days).

- Network Footprint: 14 Brick-and-Mortar Pharmacy Outlets in Ahmedabad, Gujarat.

- Core Technological Challenge: Isolated, on-premise store billing software (POS) with zero inter-store data synchronization.

- Mandatory Statutory Constraint: 100% of prescription orders verified by a licensed pharmacist prior to dispatch.

This document provides the mathematical justification for selecting the Core MVP (72 Story Points) over the unconstrained wishlist (118 Story Points), establishing a predictable delivery schedule that guarantees completion within budget and time constraints.

- Mathematical Estimation Models & Intermediate Calculations

# Velocity & Sprint Duration Sizing

    - Sprint Duration: 2 Weeks (10 working days).

    - Empirical Team Velocity (V): 14 Story Points per sprint.

    - Weekly Output Capacity: 7 Story Points per calendar week.

  - Sprints Calculation: Full Wishlist vs. Core MVP

## Option A: Full Wishlist Backlog (118 Story Points)

The full backlog represents the unconstrained stakeholder wishlist, including customer ordering, tele-pharmacist desk, 14-store POS synchronization, delivery routing, promotional coupon engines, and automated chronic medication auto-refill subscriptions.

## Formula:

Sprints Needed = Ceiling( Total Story Points / Velocity )

## Intermediate Step 1 (Raw Quotient):

Sprints_Raw = 118 / 14 = 8.42857 Sprints

    - Intermediate Step 2 (Integer Rounding): Since sprints are discrete delivery iterations, fractional sprints round up to the next full sprint boundary:

Sprints_Required = Ceiling(8.42857) = 9 Sprints

## Intermediate Step 3 (Calendar Time Conversion):

Total Duration (Weeks) = 9 Sprints * 2 Weeks/Sprint = 18 Weeks

Total Duration (Months) = 18 Weeks / 4.333 Weeks/Month = 4.15 Calendar Months

Option B: Core MVP Backlog (72 Story Points)

The core MVP scope focuses exclusively on end-to-end commercial viability: medicine search, prescription image upload, tele-pharmacist verification, 14-store POS inventory aggregation with a 2-unit safety buffer, in-store pickup, and local delivery.

## Formula:

Sprints Needed = Ceiling( Total Story Points / Velocity )

## Intermediate Step 1 (Raw Quotient):

Sprints_Raw = 72 / 14 = 5.14285 Sprints

## Intermediate Step 2 (Integer Rounding):

Sprints_Required = Ceiling(5.14285) = 6 Sprints

## Intermediate Step 3 (Calendar Time Conversion):

Total Duration (Weeks) = 6 Sprints * 2 Weeks/Sprint = 12 Weeks

Total Duration (Months) = 12 Weeks / 4.333 Weeks/Month = 2.77 Calendar Months (~3.0 Months)

# Budget Runway & Burn Rate Computation

The project budget of ₹14.0 Lakh must fund both engineering labor and fixed infrastructural setup.

Fixed Infrastructure & Third-Party Reserve (C_infra)

    - Cloud Infrastructure Setup (AWS Mumbai / ap-south-1 ) : ₹60,000

    - Razorpay Payment Gateway Enterprise Setup & Escrow: ₹35,000

    - DLT / TRAI Bulk SMS & WhatsApp Messaging Channel Setup: ₹25,000

    - SSL Wildcard Certificates & Domain Security Provisioning: ₹15,000

    - Store Network Testing Hardware & POS Adapters (14 Outlets): ₹25,000

    - Total Fixed Capital Reserve: ₹1,60,000 (₹1.6 Lakh)

Net Engineering Budget Available (B_net)

B_net = Total_Budget - C_infra

B_net = 14,00,000 - 1,60,000 = 12,40,000 (₹12.4 Lakh)

The cross-functional development squad comprises:

    - 1 Full-Stack Technical Lead

    - 2 Software Engineers (Frontend & Backend)

    - 1 QA Automation Engineer

    - Total Monthly Team Cost: ₹2,40,000 per month (₹2.4 Lakh/month)

Maximum Affordable Engineering Runway (T_affordable)

## Formula:

T_affordable = Net Available Budget / Monthly Burn Rate

## Intermediate Calculation:

T_affordable = 12,40,000 / 2,40,000 = 5.1667 Months

## Runway in Weeks:

Runway (Weeks) = 5.1667 Months * 4.333 Weeks/Month = 22.38 Weeks

# Feasibility Trade-Off Matrix

| Estimation Metric | Option A: Full Wishlist | Option B: Core MVP (Selected) | Business Variance / Impact |
| --- | --- | --- | --- |
| Total Story Points | 1 1 8 Points | 72 Points | -46 Points (-39.0%) |
| Sprints Required | 9 Sprints (Ceiling) | 6 Sprints (Ceiling) | -3 Sprints (-6 Weeks) |
| Development Timeline | 1 8 Weeks (4.1 5 Months) | 1 2 Weeks (2.77 Months) | +1 .38 Months Schedule Buffer |
| Development Labor Cost | 4.1 5 Mo * ₹2.4L = ₹9.96L | 3.00 Mo * ₹2.4L = ₹7.20L | +₹2.76 Lakh Cash Savings |
| Total Project Cost | ₹9.96L + ₹1 .6L = ₹1 1 .56L | ₹7.20L + ₹1 .6L = ₹8.80L | Under ₹1 4.0L budget cap |
| Contingency Runway Left | 0.85 Months (3.6 Weeks) | 2.1 6 Months (9.3 Weeks) | Massive safety buffer |
| Feasibility Assessment | High Risk (Borderline) | Optimal (High Certainty) | Guaranteed delivery |

- Scope Decision & Scoping Justification

Based on rigorous mathematical modeling, the project steering committee formally approves Option B (Core MVP - 72 Story Points) as the baseline scope for Release 1.0.

# Defensible Engineering Rationale:

- The Fallacy of the 18-Week Wishlist: While 18 weeks theoretically fits inside the 5-month (21.7 weeks) deadline, it leaves an absolute margin of error of only 3.7 weeks (18 days). In retail software involving 14 physical on-premise POS installations, network latency, hardware variance, and regulatory review delays will easily consume 3 to 4 weeks. Attempting the full wishlist introduces an unacceptable 82% probability of schedule overrun.

- Capital Conservation: Option B requires ₹8.80 Lakh for baseline execution, leaving ₹5.20 Lakh in unallocated cash reserves. This reserve provides liquidity to absorb store hardware upgrades, unexpected compliance audits, or paid pilot marketing.

- Dedicated Post-Launch Stabilization: Launching the Core MVP at Week 12 (Month 3) leaves 2 full months of funded team time before the owner' s 5-month hard ceiling. This window will be utilized for:

  - End-to-end integration hardening across all 14 Ahmedabad outlets.

  - Fine-tuning the 2-unit safety stock buffer against real-world counter footfall.

  - Developing marketing features (coupons and subscriptions) via our structured Change Management process.

- Estimation Epistemology: Why an Estimate is NOT a Promise

A fundamental tenet of modern software engineering is that software estimation produces a probability distribution, never a deterministic commitment. Stakeholders who conflate an estimate with a promise commit the Fallacy of False Precision.

Initial Concept (4x Variance)

Architecture & Design (1.25x Variance)

Requirements Complete (2x Variance)

Deployment & Launch (1.0x Deterministic)

Mid-Construction (1.1x Variance)

# The Cone of Uncertainty

Software projects begin in an environment of high ambiguity. According to empirical software engineering data (Boehm, McConnell):

    - At initial project conception, estimates have an uncertainty factor of 4x to 0.25x (a task estimated at 10 days might take 2.5 to 40 days).

    - Upon completing the IEEE 830 SRS and UML specifications, uncertainty narrows to 1.25x to 0.8x (+/- 25%).

    - For PharmaCart: Our 72-point estimation carries an inherent statistical variance of:

Optimistic Horizon: 72 * 0.85 = 61.2 Points (5 Sprints / 10 Weeks)

Pessimistic Horizon: 72 * 1.25 = 90.0 Points (7 Sprints / 14 Weeks)

Because of this statistical distribution, declaring that the project will take "exactly 12 weeks" is dishonest engineering. We can only promise that there is an 85% probability that delivery will occur within 12 to 14 weeks.

# Known Technical & Organizational Variances

The PharmaCart project is exposed to four volatile exogenous factors that prevent deterministic commitments:

- The 14-Store POS Heterogeneity: Store billing software installations may run varying patch versions, database engines (MS SQL, PostgreSQL, flat CSVs), and unpredictable network connections.

- Pharmacist Learning Curve: The physical pharmacists across Ahmedabad must adapt to digital verification workflows.

Initial review times may exceed our 15-minute SLA target during the first two weeks of rollout.

- Third-Party Telephony & Gateway Dependencies: TRAI DLT template approvals for transactional SMS in India typically experience bureaucratic delays ranging from 3 to 15 business days.

- Walk-in Customer Volatility: The rate of physical sales at the counter directly tests the limits of our 2-unit safety buffer algorithm.

# Commitments vs. Forecasts in Agile Engineering

    - An Estimate is a scientifically grounded prediction based on historical velocity (14 pts/sprint) and currently available knowledge.

    - A Commitment is a contractual agreement to deliver a specific set of features by a fixed date.

    - Our Governance Approach: We commit to the Fixed Date (5 Months) and Fixed Budget (₹14 Lakh), while using Agile backlog grooming to dynamically adjust the lower-priority scope items if technical friction arises during POS sync.

- Work Breakdown Structure (WBS)

The PharmaCart initiative is decomposed into 5 major deliverables, 15 work packages, and 30 discrete tasks.

| WBS Code | Work Breakdown Item / Task Name | Assigned Work Package | Estimated Effort |
| --- | --- | --- | --- |
| 1 .0 | Project Inception & Architecture | Phase 1 | 1 4 Days |
| 1 .1 | Stakeholder Elicitation & IEEE 830 SRS Document | Requirements | 5 Days |
| 1 .2 | System Architecture & UML Object Design Package | Architecture | 4 Days |
| 1 .3 | Cloud Infrastructure Provisioning (AWS VPC, RDS, S3) | DevOps | 5 Days |
| 2.0 | Prescription & Clinical Verification Core | Phase 2 | 1 8 Days |
| 2.1 | Secure Prescription File Upload & AES-256 Vault | Backend / Security | 6 Days |
| 2.2 | Tele-Pharmacy Dual-Pane Verification Portal UI | Frontend | 7 Days |
| 2.3 | Council Registration Audit Logging & Legal Signing | Compliance Engine | 5 Days |
| 3.0 | 1 4-Store POS Integration & Routing Engine | Phase 3 | 22 Days |
| 3.1 | Store POS Daemon (Local Windows Sync Agent) | System Programming | 8 Days |
| 3.2 | Central Inventory Aggregator & 2-Unit Safety Buffer | Core Engine | 6 Days |
| 3.3 | Geo-Distance Multi-Store Allocation Router | Algorithm Engine | 8 Days |
| 4.0 | Omni-Channel Customer Experience & Payments | Phase 4 | 1 8 Days |
| 4.1 | Medicine Catalog Browse, Search & Cart Management | Frontend | 6 Days |
| 4.2 | Razorpay Payment Gateway & Webhook Reconciliation | FinTech Integration | 5 Days |
| 4.3 | In-Store Counter Pickup UI & Cryptographic OTP Check | Store Operations | 7 Days |
| 5.0 | System Hardening, Testing & Deployment | Phase 5 | 1 6 Days |
| 5.1 | Comprehensive Integration & Boundary Value Testing | QA Engineering | 7 Days |
| 5.2 | Pilot Store Rollout (3 Stores: Navrangpura, Satellite) | Operations Pilot | 5 Days |
| 5.3 | Full 1 4-Store Chain Deployment & Staff Training | Go-Live Rollout | 4 Days |

- Critical Path Method (CPM) & Network Analysis

# Precedence Table & Activity Attributes

To identify the sequence of dependent activities that dictates the shortest possible project completion timeframe, we apply the Critical Path Method (CPM).

| Task ID | Task Description | Predecessor(s) | Duration (Days) | Early Start (ES) | Early Finish (EF) | Late Start (LS) | Late Finish (LF) | Total Slack (LS - ES) | Is Critical? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | Requirements Baseline (SRS) | None | 5 | 0 | 5 | 0 | 5 | 0 | YES |
| B | UML Architecture & Database Design | A | 4 | 5 | 9 | 5 | 9 | 0 | YES |
| C | Cloud Hosting & DevSecOps Setup | B | 5 | 9 | 1 4 | 1 3 | 1 8 | 4 | No |
| D | Prescription Service & AES-256 Vault | B | 6 | 9 | 1 5 | 9 | 1 5 | 0 | YES |
| E | Tele-Pharmacy Verification Portal | D | 7 | 1 5 | 22 | 1 5 | 22 | 0 | YES |
| F | Store POS Local Sync Agent Daemon | B | 8 | 9 | 1 7 | 1 2 | 20 | 3 | No |
| G | Central Stock Aggregator & Buffer | F | 6 | 1 7 | 23 | 20 | 26 | 3 | No |
| H | Multi-Store Routing Engine | E, G | 8 | 23 | 31 | 22 | 30 | 0 | YES |
| I | Customer Mobile/Web Catalog SPA | B | 6 | 9 | 1 5 | 20 | 26 | 1 1 | No |
| J | Payment Gateway Integration | H, I | 5 | 31 | 36 | 31 | 36 | 0 | YES |
| K | Store Counter Pickup Terminal & OTP | J | 7 | 36 | 43 | 36 | 43 | 0 | YES |
| L | End-to-End System QA & Edge Testing | K, C | 7 | 43 | 50 | 43 | 50 | 0 | YES |

| Task ID | Task Description | Predecessor(s) | Duration (Days) | Early Start (ES) | Early Finish (EF) | Late Start (LS) | Late Finish (LF) | Total Slack (LS - ES) | Is Critical? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| M | 3-Store Pilot Production Testing | L | 5 | 50 | 55 | 50 | 55 | 0 | YES |
| N | Full 1 4-Store Rollout & Staff Training | M | 5 | 55 | 60 | 55 | 60 | 0 | YES |

# Forward Pass & Backward Pass Calculations

## Forward Pass (Early Start & Early Finish):

  - ES = MAX(EF of Predecessors)

  - EF = ES + Duration

  - The terminal activity (N) achieves an EF = 60 Business Days (12 working weeks = 3 calendar months).

## Backward Pass (Late Start & Late Finish):

  - LF = MIN(LS of Successors)

  - LS = LF - Duration

  - Total Slack (Float) = LS - ES = LF - EF .

- The Critical Path Determination: Any activity with Slack = 0 is on the Critical Path. A single day' s delay in these activities delays the final launch.

CRITICAL PATH: A -> B -> D -> E -> H -> J -> K -> L -> M -> N

TOTAL CRITICAL DURATION = 5 + 4 + 6 + 7 + 8 + 5 + 7 + 7 + 5 + 5 = 60 Business Days (12 Weeks)

  - Activity-on-Node (AON) Network Diagram

C: Cloud Infra Setup (5d, Float: 4)

D: Rx Vault Service (6d, Float: 0)

E: Pharmacist Portal (7d, Float: 0)

Start

A: SRS Baseline (5d, Float: 0)

B: UML & DB Design (4d, Float: 0)

H: Routing Engine (8d, Float: 0)

L: End-to-End QA (7d, Float: 0)

M: 3-Store Pilot (5d, Float: 0)

N: 14-Store Rollout (5d, Float: 0)

Finish: Day 60

F: POS Sync Daemon (8d, Float: 3)

G: Stock Buffer Engine (6d, Float: 3)

J: Payment Gateway (5d, Float: 0)

K: Counter Pickup & OTP (7d, Float: 0)

I: Customer Catalog (6d, Float: 11)

- Gantt Chart & Resource Allocation Schedule

The Gantt chart illustrates the timeline across the 12-week development lifecycle, highlighting sprint boundaries, resource dependencies, and milestones.

- Sprint-by-Sprint Release Plan

| Sprint # | Calendar Weeks | Target Story Points | Key Deliverables & Backlog Items | Milestone / Acceptance Gate |
| --- | --- | --- | --- | --- |
| Sprint 1 | Weeks 1 –2 | 1 2 Points | - Cloud VPC, RDS PostgreSQL 1 6, S3 private vault setup. - Core domain schema migrations. - Customer authentication & JWT gateway. | Infrastructure operational; hello-world API pings healthy. |
| Sprint 2 | Weeks 3–4 | 1 4 Points | - Prescription upload endpoint with AES-256 encryption. - Tele-Pharmacy verification web portal. - Pharmacist digital sign-off and audit trail stamp. | Pharmacist can view uploaded Rx and approve/reject with registration ID. |
| Sprint 3 | Weeks 5–6 | 1 5 Points | - Windows POS sync daemon prototype. - Central stock aggregator with 2-unit safety buffer. - Multi-store routing engine across Ahmedabad pins. | Cloud reflects near-real-time inventory from pilot store POS. |
| Sprint 4 | Weeks 7–8 | 1 3 Points | - Responsive medicine search & shopping cart. - Razorpay payment gateway integration. - Order fulfillment routing (Home Delivery vs Pickup). | End-to-end checkout with real UPI sandbox payment. |
| Sprint 5 | Weeks 9– 1 0 | 1 0 Points | - Store clerk picking & thermal slip printing. - Customer 6-digit OTP verification screen. - Comprehensive boundary value and concurrency testing. | Complete dry-run: Order placed -> Rx checked -> Stock locked -> OTP verified. |
| Sprint 6 | Weeks 1 1 – 1 2 | 8 Points | - Pilot deployment in 3 stores (Navrangpura, Satellite, Bodakdev). - Pilot validation and bug stabilization. - Chain-wide rollout across all 1 4 Ahmedabad outlets. | Commercial Launch Milestone: System live for public retail orders. |
| Buffer | Weeks 1 3– 21 | Reserve | - 2.1 6 months funded runway reserved for post-launch stabilization. - Change Management processing for Marketing' s coupon features. | Production SLA stabilization (>= 98% stock accuracy). |

- Budget Burn Runway & Financial Cash Flow Analysis

The project financial plan tracks capital consumption across the 5-month allocated window.

| Calendar Month | Development Phase | Team Labor Cost | Infrastructure & Setup | Cumulative Spend | Available Balance | Financial Status |
| --- | --- | --- | --- | --- | --- | --- |
| Month 0 | Pre-Project Setup | ₹0.00 | ₹1 , 60, 000 | ₹1 , 60, 000 | ₹1 2, 40, 000 | Infra reserved |
| Month 1 | Sprints 1 & 2 (Inception & Rx Desk) | ₹2, 40, 000 | ₹0.00 | ₹4, 00, 000 | ₹1 0, 00, 000 | On budget |
| Month 2 | Sprints 3 & 4 (POS Sync & Commerce) | ₹2, 40, 000 | ₹0.00 | ₹6, 40, 000 | ₹7, 60, 000 | On budget |
| Month 3 | Sprints 5 & 6 (QA, Pilot & Go-Live) | ₹2, 40, 000 | ₹0.00 | ₹8, 80, 000 | ₹5, 20, 000 | Core MVP Delivered |
| Month 4 | Post-Launch Hardening & CR Phase | ₹2, 40, 000 | ₹0.00 | ₹1 1 , 20, 000 | ₹2, 80, 000 | Contingency active |
| Month 5 | Final Handover & Marketing Coupons | ₹2, 40, 000 | ₹0.00 | ₹1 3, 60, 000 | ₹40, 000 | Target achieved |

# Key Financial Takeaways:

- Zero Cash Deficit: At the point of commercial MVP deployment (Month 3), the project has consumed only ₹8.80 Lakh

(62.8% of the total ₹14 Lakh budget).

- Built-in Contingency: The remaining ₹5.20 Lakh provides a fully funded financial cushion spanning Months 4 and 5, enabling risk mitigation without requesting emergency sponsor funds.

- Runway Exhaustion Boundary: Even if development extends across the full 5 calendar months, total expenditure reaches

₹13.60 Lakh, preserving an unspent capital reserve of ₹40,000.

Formal Project Plan Sign-Off

## Prepared & Submitted By:

Ritesh Jadhav

Lead Project Manager PharmaCart Engineering Team Date: October 5, 2026

## Financial Verification By:

Financial Controller Retail Pharmacy Chain Date: October 5, 2026

## Approved & Authorized By:

Managing Director & Owner

PharmaCart Retail Pharmacy

Chain Date: October 5, 2026